## Sheet1
| W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17
Work Conception and Initiation | bar: W1
Finalize problem statement | bar: W2
Understand project | bar: W2
Finalize Technology Stack | bar: W2
Requirement Gathering and learning technologies | bar: W3
Complete test project | bar: W4
Traffic Intensity Prediction and Recommendation – Main Project
Research in traffic intensity prediction and factors to recommend road-widening | bar: W5 to W6
Programming prediction and recommendation logic in python | bar: W7 to W8
Building prediction and recommendation UI | bar: W9 to W11
User Management (UI)
Signup based user registration | bar: W12
Registration UI | bar: W13
Approval by Admin UI | bar: W13 to W14
Non-signup based user registration | bar: W15
Creation of user by Admin | bar: W15
Testing and Deployment | bar: W16 to W17